## VFF_RTM
Project | VFF Integrated Management System (IMS)
Team Members | S/21/444, S/21/145, S/21/029, S/21/301
Date | 27/02/2026
Version | 1.0
ID | Requirements | Specifications | Biz Needs/Objectives/Goals | Requested By | Dept. | WBS/Deliverables | Test Cases | Status | Comments
FR-REQ-5.1 | User Authentication & RBAC | Secure login with role-based access control | Ensure data security and controlled access | Project Sponsor (VFF Director) | Admin/IT | Security Module | FT-9.1 | Planned | Critical security requirement. Must be implemented before any module testing.
FR-REQ-5.2 | Employee Profile Management | CRUD management of staff records | Centralized HR data management | HR Lead | HR | HR Module | FT-9.2 | Planned | Foundation module for payroll dependency.
FR-REQ-5.3 | Daily Attendance Auto-Locking | Immutable attendance after submission | Eliminate payroll manipulation risk | HR Lead | HR | HR Module | FT-9.2 | Planned | Ensures payroll integrity through immutable attendance.
FR-REQ-5.4 | Automated Payroll Engine | Rule-based payroll calculation using locked attendance | Reduce manual payroll errors | Finance Lead | Finance | Finance Module | FT-9.3 | Planned | Core financial automation feature with strict rule enforcement.
FR-REQ-5.5 | Cash vs Receivables Dashboard | Real-time liquidity visualization | Prevent liquidity confusion | Finance Lead | Finance | Finance Dashboard | FT-9.4 | Planned | Directly addresses liquidity risk identified in project charter.
FR-REQ-5.7 | Program-Centric Inventory | Stock issuance linked to programs | Track operational cost allocation | Operations Lead | Operations | Inventory Module | FT-9.5 | Planned | Links physical inventory to financial cost allocation.
FR-REQ-5.9 | Cost-Per-Animal Metric | Automated cost efficiency calculation | Measure program sustainability | Operations Lead | Operations | Analytics Engine | FT-9.6 | Planned | Key analytical metric supporting program sustainability.
FR-REQ-5.11 | System Audit Logging | Immutable audit trail for critical actions | Ensure accountability and compliance | Admin & QA Lead | Admin | Security Layer | FT-9.8 | Planned | Required for compliance, traceability, and audit readiness.
NF-SEC-1.1 | Encrypted Communication | Secure credential transmission & hashing | Protect sensitive employee & financial data | Admin & QA Lead | Admin | Security Layer | NFR-TC-02 | Planned | Mandatory encryption to protect financial and employee data.
NF-AVA-1.1 | System Availability | 95% uptime during working hours | Ensure operational continuity | Project Sponsor | IT | Infrastructure | NFR-TC-03 | Planned | Ensures operational continuity during working hours.